## Sheet1
Phase | Component | Objective | Deliverables | Status
1 | Query Understanding & Routing Agent | Classify user queries and route to appropriate agent | LangChain agent setup + routing logic + Gemini LLM | done
2 | PAQ Knowledge Base (FAQ Agent) | Retrieve past questions & responses | Vector DB integration, retrieval tool, FAQ tool integration | done
3 | Forecasting Agent | Predict future demand using Nykaa_Dataset.csv | XGBoost-based predictor using region, category, etc. | done
4 | Competitor Analysis Agent | Compare Nykaa products with competitor data from Competitor_Dataset.csv | Fuzzy matching + competitor comparison tool | Basic done gemini integration+web search + response human type
5 | Market Watcher Agent | Get market trends (internal tabular + web) | Tabular trends + web search fallback + fuzzy matcher | ⏳
6 | Website Search Agent | Answer general queries using web search | Gemini-powered web search via LangChain tool | ⏳
7 | Multi-Agent Collaboration | Seamless coordination of Forecasting, Market, Competitor agents | Integrated logic to handle complex multi-agent queries | ⏳
8 | Conversational UI | Build frontend with human-like chat | LangChain + Gemini-powered interface (Streamlit or Web UI) | ⏳
9 | Testing & Examples | Cover edge cases, add test queries for each agent | Test harness + logs + known queries for validation | ⏳
10 | Deployment Ready Bundle | Final package with modular code | Streamlit App, modular agents, documentation | ⏳